## Slide 1
PROJECT BLUEPRINT — APRIL 2026
Alhuda 2.0
Platform Launch — Full Execution Plan
10
PHASES
7,277+
HADITHS
$0
INFRA COST
~14
DAYS TO LAUNCH

## Slide 2
WHAT WE ARE BUILDING
Platform Overview
→
Codebase Clone
Fork timeless-hadith GitHub repo into a new
Alhuda 2.0 repository — zero rebuild required.
⬡
New Supabase DB
Fresh PostgreSQL project. Same schema.
You provide credentials before Phase 1 begins.
☁
Cloudflare Pages
Separate CF Pages project auto-deploys on
every push to main. Free global CDN.
◈
Full Rebrand
New name, logo, color palette, favicon, and
all copy updated throughout the codebase.
✦
AI Hadith Search
GPT-4o-mini hybrid search: full-text +
semantic. Fast, grounded, hallucination-free.
⊕
Custom Domain
New domain with Cloudflare SSL and CDN.
Configured and live on launch day.

## Slide 3
TECHNOLOGY
Full Stack
Cloudflare Pages
Edge hosting, auto-deploy,
free SSL + global CDN
Supabase PostgreSQL
New project, same schema.
RLS, REST, Auth.
OpenAI GPT-4o-mini
AI search & content.
User provides API key.
Supabase Auth
Email/password, JWT sessions.
Replaces Firebase Auth.
Web Speech API
Browser-native voice reading.
Free, no API cost.
GitHub Actions
CI validation before every
Cloudflare deployment.

## Slide 4
00
Repository Setup & Codebase Clone
Day 1 · Fork Timeless Hadith — create the Alhuda 2.0 GitHub repo
PHASE 00
1
Create new GitHub repository
Create `alhuda-2-0` under the ehsaasradio-bot account. Initialize with README.
2
Clone Timeless Hadith codebase
Clone timeless-hadith locally, strip git history, push as clean initial commit to new repo.
3
Set branch strategy
Create main (production) and develop (staging). Protect main with PR-only merges.
4
Copy & adapt CLAUDE.md
New CLAUDE.md for Alhuda 2.0 with updated project name, domain, Supabase URL (TBD).
git commit: chore(init): initial alhuda-2-0 repo from timeless-hadith base

## Slide 5
01
Supabase Project Creation
Day 1–2 · New database — user provides credentials before work begins
PHASE 01
1
Create new Supabase project
Go to supabase.com → New Project → Name it 'alhuda-2'. Save the project URL and anon key.
2
Share credentials with Claude
Required: Supabase URL, Anon Key, Service Role Key. Stored only in Cloudflare env vars — never in code.
3
Run schema migration
Export SQL from Timeless Hadith Supabase and import into new project. Tables: hadiths, blog_posts, bookmarks, categories.
4
Configure RLS + Enable Auth
Row Level Security: public read on hadiths. Auth-required write for bookmarks. Enable email/password auth, disable Firebase.
REQUIRED FROM YOU
— Supabase Project URL
— Supabase Anon (public) Key
— Supabase Service Role Key
— Migrate data from TH? Yes / No
git commit: feat(db): supabase schema, rls, and auth configured

## Slide 6
02
Branding & Identity Overhaul
Day 2–3 · Rename, re-logo, recolor — every trace of Timeless Hadith updated
PHASE 02
1
Global find & replace: site name
Replace all instances of 'Timeless Hadith' with 'Alhuda' across HTML, JS, CSS, meta tags, OG tags, footer.
2
Replace logo assets
User provides new Alhuda 2.0 logo. Replace navbar, mobile header, footer, PWA manifest. Update favicon.
3
Update color palette (optional)
If Alhuda needs a different identity, update CSS variables for light and dark mode. Suggested: forest green + gold.
4
Update manifest and PWA metadata
Update manifest.json: new name, short_name, theme_color, and icon paths. Correct PWA install screen on mobile.
ASSETS REQUIRED FROM YOU
— Alhuda 2.0 logo (SVG/PNG, 512px+)
— Favicon (ICO/PNG, 32×32 + 192×192)
— Color scheme preference
— Site tagline for meta description
git commit: feat(brand): rebrand all assets and copy to alhuda-2-0

## Slide 7
03
Environment Variables & Configuration
Day 3 · Wire new Supabase credentials into the codebase safely
PHASE 03
1
Update Supabase config in JS
Replace Timeless Hadith Supabase URL and anon key with Alhuda 2.0 credentials in the frontend config file.
2
Verify no secrets in codebase
Run grep scan for API keys and tokens. Only the anon (public-safe) key in JS. Service role key to Cloudflare env vars only.
3
Update GitHub Actions CI
Add Alhuda 2.0 secrets to GitHub Actions. Update workflow files with new repo name references.
git commit: chore(config): update supabase config and remove legacy credentials

## Slide 8
04
Cloudflare Pages Deployment
Day 3–4 · New Cloudflare project — auto-deploy from Alhuda 2.0 repo
PHASE 04
1
Create new Cloudflare Pages project
CF Dashboard → Pages → Create → Connect GitHub → Select alhuda-2-0 → Branch: main. Build command: none (static site).
2
Add environment variables
In CF Pages settings add: SUPABASE_URL, SUPABASE_ANON_KEY, OPENAI_API_KEY, SUPABASE_SERVICE_ROLE_KEY.
3
Test initial deployment
Verify alhuda-2-0.pages.dev loads correctly. Check console for errors. Confirm Supabase connection works.
4
Configure custom domain
CF Pages → Custom Domains → add your Alhuda domain. Update DNS A/CNAME. SSL auto-provisions within minutes.
REQUIRED FROM YOU
— Cloudflare account access
— GitHub OAuth for CF Pages
— Domain name for Alhuda 2.0
— DNS registrar access (Namecheap etc.)
git commit: chore(deploy): cloudflare pages configured and domain live

## Slide 9
05
Data Migration
Day 4–6 · Import hadith data into the new Alhuda 2.0 Supabase database
PHASE 05
1
Export data from Timeless Hadith
Use Supabase dashboard or pg_dump to export hadiths table (7,277 rows) as SQL dump or CSV. Also export categories, blog posts.
2
Import into Alhuda 2.0 Supabase
Use Supabase SQL editor or psql to import. Verify row counts match. Check encoding — Arabic text must be preserved in UTF-8.
3
Rebuild full-text search indexes
Run tsvector update queries on the hadiths table to rebuild search indexes for both English and Arabic columns.
4
Verify data on the frontend
Open live Alhuda 2.0 site and confirm hadiths, categories, and search results load correctly from the new database.
git commit: feat(data): hadith data migrated and search indexes rebuilt

## Slide 10
06
UI/UX & Content Cleanup
Day 6–8 · Remove Timeless Hadith content, refine Alhuda identity
PHASE 06
1
Rewrite About Us page
Fresh About Us for Alhuda 2.0: new mission, vision, authentic hadith value, user trust — distinct from Timeless Hadith.
2
Update footer, legal, contact
New copyright name and year. Update privacy policy and terms of service. New contact email for Alhuda.
3
Remove Timeless Hadith social links
Update or remove existing social links. Add Alhuda-specific profiles: Facebook, Instagram, X, YouTube, LinkedIn.
4
Apply sprint-level UI improvements
Carry over improvements from TH sprint: emoji removal, italic cleanup, theme system, bookmark badge, category icons.
git commit: feat(content): alhuda-2-0 about page, footer, and ui cleanup

## Slide 11
07
SEO Optimization
Day 8–9 · Rank Alhuda 2.0 from day one with structured metadata
PHASE 07
1
Update all page titles & meta descriptions
Every page gets a unique, keyword-rich title and meta description reflecting Alhuda's identity and hadith content.
2
Add Open Graph and Twitter Card tags
OG image, OG title, OG description, Twitter:card — rich previews when shared on social media.
3
Add JSON-LD structured data
WebSite schema on homepage. BreadcrumbList on category pages. Article schema on blog posts.
4
Submit sitemap to Google Search Console
Add domain to Google Search Console. Submit sitemap.xml. Request indexing of key pages immediately after launch.
git commit: feat(seo): metadata, og tags, json-ld, and sitemap configured

## Slide 12
08
AI-Powered Search Integration
Day 9–11 · Connect OpenAI for hybrid semantic + full-text hadith search
PHASE 08
1
Connect OpenAI API key
User provides OpenAI API key. Add to Cloudflare Pages env vars. Configure model: gpt-4o-mini for cost efficiency.
2
Generate and store embeddings
Optional: generate text-embedding-3-small embeddings per hadith stored in Supabase pgvector column. Enables semantic retrieval.
3
Wire up hybrid search endpoint
Supabase Edge Function: run full-text tsvector query first, then re-rank using semantic similarity. Return top 10 results.
4
Test search quality
Test queries in English and Arabic. Verify results are relevant, fast (<2s), and grounded — no hallucinated content.
REQUIRED FROM YOU
— OpenAI API key
— Enable embeddings? Yes / No
— Budget alert threshold
— Social automation choice
git commit: feat(ai): openai hybrid search integrated for alhuda-2-0

## Slide 13
09
Final QA, Performance & Go-Live
Day 12–14 · Full testing pass, Lighthouse audit, and launch
PHASE 09
1
Cross-device QA
Test on mobile (iOS + Android), tablet, and desktop. Check layout, theme toggle, bookmarks, search, and navigation.
2
Lighthouse performance audit
Run Lighthouse on key pages. Target: Performance 90+, SEO 90+, Accessibility 85+, Best Practices 90+.
3
Security check
Confirm no secrets in frontend JS. Verify Supabase RLS blocks unauthorized writes. Check CORS and CSP headers via Cloudflare.
4
DNS propagation & launch
Verify custom domain is fully propagated. Test HTTPS. Announce on social media. Submit to Google Search Console immediately.
git commit: chore(qa): final polish, performance, and launch ready

## Slide 14
SCHEDULE
14-Day Timeline
Phase
Name
Days
Blocker
Status
Phase 0
Repo Setup & Clone
Day 1
—
Ready
Phase 1
Supabase Project Setup
Day 1–2
Need credentials
Input
Phase 2
Branding & Identity
Day 2–3
Need logo assets
Input
Phase 3
Env Variables & Config
Day 3
After Phase 1
Blocked
Phase 4
Cloudflare Pages Deploy
Day 3–4
Need domain + CF
Input
Phase 5
Data Migration
Day 4–6
After Phase 1 & 3
Blocked
Phase 6
UI/UX & Content Cleanup
Day 6–8
—
Parallel
Phase 7
SEO Optimization
Day 8–9
After Phase 6
Blocked
Phase 8
AI Search Integration
Day 9–11
Need OpenAI key
Input
Phase 9
QA, Performance & Launch
Day 12–14
After all phases
Final

## Slide 15
BEFORE WE START
What You Need to Provide
Supabase (Phase 1)
New Supabase project URL
Anon (public) Key
Service Role Key
Migrate TH data? Yes / No
Branding (Phase 2)
Logo file (SVG/PNG 512px+)
Favicon ICO/PNG
Color scheme preference
Site tagline text
Deployment (Phase 4)
Cloudflare account access
GitHub OAuth for CF Pages
Domain name for Alhuda 2.0
DNS registrar access
AI Features (Phase 8)
OpenAI API key
Enable embeddings? Yes / No
OpenAI budget alert threshold
Social automation: Buffer or Make.com

## Slide 16
Ready to Build
Alhuda 2.0
Provide your Supabase credentials, logo, domain, and OpenAI key
and Claude will execute all 10 phases from Day 1.
Remember: Choose social automation at the end · Buffer ($6/mo) or Make.com ($9/mo)
Prepared by Claude (Cowork Mode) · April 2026