## Slide 1
REMEDIATION ROADMAP 2026
Fix It.
Ship It. Own It.
A prioritised, actionable remediation plan across Security, SEO, Performance & Best Practices for timelesshadith.com
21
Total Findings
4
Critical
7
High Priority
90
Days to Close
timelesshadith.com · April 2026

## Slide 2
Executive Summary
21 findings identified across 4 domains. No changes implemented — this is a plan only.
4
Critical
Act within 24 hours
7
High
Complete within 2 weeks
8
Medium
Complete within 60 days
2
Low
Polish within 90 days
FINDINGS BY CATEGORY
Security
11
SEO
5
Performance
3
Best Practices / PWA
2
timelesshadith.com · Remediation Plan · April 2026

## Slide 3
CRITICAL
4 Findings — Act Within 24 Hours
C-01
Security
Admin CMS Accessible Without Auth
sessionStorage gate trivially bypassed. HTTP 200 to all visitors. Full admin panel exposed.
Estimated effort:
2–3 hrs
24-48 hrs deadline
C-02
Security
Password Hash Hardcoded in Public HTML
SHA-256 hash visible in page source. No salt. Recoverable via crackstation.net instantly.
Estimated effort:
1 hr
24-48 hrs deadline
C-03
Security
Supabase Key in 4 Files + GitHub
7,277 hadiths exposed. 10-year JWT hardcoded in public repo — rotate immediately.
Estimated effort:
3–4 hrs
24-48 hrs deadline
C-04
SEO
Sitemap Slug Mismatch — 97 URLs Broken
sitemap.xml uses book-N IDs. Live site uses semantic slugs. 97/102 pages may be un-indexed.
Estimated effort:
2 hrs
24-48 hrs deadline
timelesshadith.com · Remediation Plan · April 2026

## Slide 4
HIGH PRIORITY
7 Findings — Complete Within 2 Weeks
H-01
10-Year JWT Validity
Security
Effort: 1 hr
Week 1
H-02
CORS Wildcard on All Routes
Security
Effort: 30 min
Week 1
H-03
Legacy Firebase Still Loading
Security / Perf
Effort: 2 hrs
Week 1
H-04
Missing DMARC / SPF Softfail
Security
Effort: 30 min
Week 1
H-05
4 Render-Blocking JS Files
Performance
Effort: 30 min
Week 1
H-06
No WebP Images (All PNG)
Performance / SEO
Effort: 2–4 hrs
Week 2
H-07
JS Bundle Not Minified (79.5KB)
Performance
Effort: 2 hrs
Week 2
timelesshadith.com · Remediation Plan · April 2026

## Slide 5
MEDIUM & LOW
10 Findings — Complete Within 60–90 Days
MEDIUM — Month 2
M-01
CSP unsafe-inline in Headers
Security
M-02
No SRI on External Scripts
Security
M-03
robots.txt Exposes Admin Paths
Security
M-04
No Rate Limiting on AI API
Security
M-05
Meta Descriptions Too Long
SEO
M-06
JS/CSS Cache TTL Only 4 Hours
Performance
M-07
Schema.org Missing on Key Pages
SEO
M-08
No Service Worker (PWA Incomplete)
PWA
LOW — Month 3
L-01
font-display:swap Missing on Google Fonts
Effort: 5 min
L-02
Only 1 of 3 Images Uses Lazy Loading
Effort: 15 min
Quick Wins Available
These low items take under 20 minutes combined — ship them in your very next deploy:
Add &display=swap to Google Fonts URL — 5 min
Add loading="lazy" to remaining images — 5 min
Remove admin paths from robots.txt — 5 min
Update meta descriptions to under 150 chars
Set JS/CSS Cache-Control to 1 year — 5 min
timelesshadith.com · Remediation Plan · April 2026

## Slide 6
PRIORITISATION
Effort vs Impact Matrix
HIGH IMPACT — LOW EFFORT
Start here — biggest bang for your hour
Fix sitemap slugs (C-04)
Remove password hash (C-02)
Add defer to scripts (H-05)
DMARC + SPF fix (H-04)
Fix CORS wildcard (H-02)
Remove admin from robots.txt (M-03)
HIGH IMPACT — HIGH EFFORT
Schedule these — critical but need planning
Real CMS server-side auth (C-01)
Rotate Supabase key (C-03)
Remove Firebase SDK (H-03)
Convert images to WebP (H-06)
Minify JS bundle (H-07)
Remove CSP unsafe-inline (M-01)
LOWER IMPACT — LOW EFFORT
Fill gaps when time allows
JWT expiry to 30 days (H-01)
Rate limit AI API (M-04)
font-display:swap (L-01)
Lazy load all images (L-02)
LOWER IMPACT — HIGH EFFORT
Nice to have — do last
SRI on external scripts (M-02)
Service Worker / PWA (M-08)
Full Schema.org markup (M-07)
timelesshadith.com · Remediation Plan · April 2026

## Slide 7
IMPLEMENTATION ROADMAP
30 · 60 · 90 Day Plan
PHASE 1
Days 1–30
Stop the bleeding
Rotate Supabase anon key & move to env vars
Implement real server-side CMS auth
Remove hardcoded password hash from HTML
Fix 97 sitemap slugs & resubmit to GSC
Add DMARC record + harden SPF to -all
Fix CORS wildcard for admin paths
Remove Firebase SDK / add defer to scripts
Configure JWT expiry to 30 days
PHASE 2
Days 31–60
Optimise & harden
Convert 16 PNG images to WebP format
Minify JS bundle with Terser (save ~30KB)
Tighten CSP — remove unsafe-inline
Add SRI to all external scripts
Rate-limit AI search endpoint (Cloudflare)
Add Quotation & BreadcrumbList schema
Fix meta description lengths (all pages)
Set JS/CSS cache TTL to 1 year
PHASE 3
Days 61–90
Level up & grow
Implement Service Worker for offline PWA
Self-host Inter font + font-display:swap
Lazy load all below-fold images
Enable Cloudflare Polish (auto WebP/AVIF)
Run Rich Results Test & fix schema gaps
Connect Supabase to live frontend
Choose social automation tool
Target Lighthouse 90+ across all pages
timelesshadith.com · Remediation Plan · April 2026

## Slide 8
EFFORT REFERENCE
Complete Effort & Timeline Table
ID
FINDING
CATEGORY
SEV
TIME
TARGET
C-01
CMS admin auth bypass
Security
Critical
2–3 hrs
24 hrs
C-02
Password hash in public HTML
Security
Critical
1 hr
24 hrs
C-03
Supabase key in 4 files + GitHub
Security
Critical
3–4 hrs
24 hrs
C-04
Sitemap slug mismatch (97 URLs)
SEO
Critical
2 hrs
48 hrs
H-01
10-year JWT validity window
Security
High
1 hr
Week 1
H-02
CORS wildcard on all routes
Security
High
30 min
Week 1
H-03
Legacy Firebase still loading
Security / Perf
High
2 hrs
Week 1
H-04
Missing DMARC / SPF softfail
Security
High
30 min
Week 1
H-05
4 render-blocking JS files
Performance
High
30 min
Week 1
H-06
No WebP images (all PNG)
Performance
High
2–4 hrs
Week 2
H-07
JS not minified (79.5KB)
Performance
High
2 hrs
Week 2
M-01
CSP unsafe-inline in headers
Security
Medium
4–6 hrs
Month 2
M-02
No SRI on external scripts
Security
Medium
2 hrs
Month 2
M-03
robots.txt exposes admin paths
Security
Medium
15 min
Month 2
M-04
No rate limiting on AI API
Security
Medium
1 hr
Month 2
M-05
Meta descriptions too long
SEO
Medium
30 min
Month 2
M-06
JS/CSS cache TTL 4 hours only
Performance
Medium
1 hr
Month 2
M-07
Schema.org missing on key pages
SEO
Medium
4 hrs
Month 2
M-08
No Service Worker (PWA)
Best Practices
Medium
3–5 hrs
Month 2
L-01
font-display:swap missing
Performance / SEO
Low
5 min
Month 3
L-02
Only 1 image lazy-loaded
Performance
Low
15 min
Month 3
timelesshadith.com · Remediation Plan · April 2026

## Slide 9
NEXT STEPS
Ready to
Implement?
01
Approve this plan
Confirm scope, priority order, and any adjustments before implementation begins.
02
Start with Critical fixes
The 4 critical items take ~8 hours combined. Rotate the Supabase key today — no waiting.
03
Deploy High priority in Week 1
defer scripts, remove Firebase, fix CORS and DMARC — all under 30 minutes each.
04
Schedule Month 2 work
WebP conversion, JS minification, CSP hardening — plan as a focused sprint.
Remember
No code has been touched yet.
All findings are documented.
Implement only when you say go.
Social Media Tool Choice:
Buffer ($6/mo) — simplest
Make.com ($9/mo) — most flexible
Target: Lighthouse 90+
across all pages by Day 90.
timelesshadith.com · Remediation Plan · April 2026 · Plan only — no changes implemented